## Sheet1
S. No. | App | Module | Sub-module | Description | Screenshot | Status | Comment (Developer) | Comment (QA)
1 | Admin | Login |  | Text being overlapped | https://prnt.sc/UsSTckL_DgQV | Closed |  | The UI issue with overlapping text on the login page has been documented with a screenshot and assigned a New status for developer review.
2 | Admin | Dashboard |  | Dashboard card are not clickable |  | Closed
3 | Admin | Dashboard | Recent order | View all oders not clickable |  | Closed
4 | Admin | Favicon |  | Favicon should match app logo |  | Closed
5 | Admin | Header |  | Header should be pinned |  | Reopen
6 | Admin | Header | SignOut | Sigging out should as for confirmation |  | Closed
7 | Admin | Header |  | Search bar is not functional |  | Reopen
8 | Admin | Menu bar |  | clicking menu bar icon should redirect user to the dashboard page |  | Closed
9 | Admin | Login |  | Login --> dashboard --> user should not return to login page on clicking back once logged in |  | Closed
10 | Admin | Dashboard |  | seller icon is different in menu bar as compared to dashboard |  | Closed
11 | Admin | Dashboard | Earnings | click graph --> graph start to appear with in a box |  | Closed
12 | Admin | Dashboard | top categorties | click pie chart --> chart start to appear with in a box |  | Closed
13 | Admin | Dashboard | Recent order | Order ID is too long |  | Reopen
14 | Admin | Dashboard | Recent order | View all orders is not clickable |  | Closed
15 | Admin | Dashboard | Top product | View all products is not clickable |  | Closed
16 | Admin | Dashboard | Recent order | Time should show date and time |  | Closed
17 | Admin | Dashboard |  | Total user card show Inaccurate info |  | Closed
18 | Admin | My Profile |  | Hovering over profile picture gives camera icon but do not give option to add picture |  | Closed
19 | Admin | Categories | All categories | search bar placeholder should be search category |  | Reopen
20 | Admin | Categories | Header categories | add new header --> entering invalid hex code should give validation error |  | Closed
21 | Admin | Categories | Header categories | add new header --> name field should give validation error on entering only special character |  | Closed
22 | Admin | Categories | Header categories | Add new header --> create header --> failded to create message displayed without reason (it happend because i used duplicate name so it should let admin know that such category already exist) |  | Resolved
23 | Admin | Products |  | Product cards except all item shows info of only products within that pagination |  | Resolved
24 | Admin | Products | Product list | Approved product still shows approve button in actions |  | Reopen
25 | Admin | Products | Product list | Action --> edit --> photos --> added gallery photo than deleted --> save changes --> the main cover photo changes with that deleted photo |  | Resolved
26 | Admin | Products | Product list | Action --> edit --> item varients --> stock should not be in negative |  | Reopen
27 | Admin | Products | Product list | Stock of All varients of product are >50 still the low stock status is not updated |  | Resolved
28 | Admin | Products | Filter | click show all filter --> only live is not visible |  | Reopen
29 | Admin | Products |  | there should be filter for low stock and out of stock not just count |  | Reopen
30 | Admin | Customer |  | Add new customer button is not functional |  | Reopen
31 | Admin |  |  | all pages should open from top -->each page should have individual scroll |  | Reopen
32 | Admin |  |  | Admin should receive notification of requests if seller make changes in product |  | Resolved
33 | Admin | Marketing tools | Hero & categories per page | list resuffel on refreshing (should be in order as visible in user app) |  | Reopen
34 | Admin | Marketing tools | coupons & promos | create new promo --> discount value, min order requirement, max discount and total uses goes negative |  | Resolved
35 | Admin | Marketing tools | coupons & promos | create new promo --> discount value goes above 100 when discount kind is percent |  | Resolved
36 | Admin | Marketing tools | coupons & promos | Performance is not updating |  | Resolved
37 | Admin | Marketing tools | coupons & promos | Per user limit and total uses is not working |  | Resolved
38 | Admin | Marketing tools | coupons & promos | Expired coupon status is not updated |  | Resolved
39 | Admin | Marketing tools | coupons & promos | Failed to delete coupon |  | Resolved
40 | Admin |  |  | Date format across the whole panel should DD/MM/YYYY |  | Resolved
41 | Admin | Customer support | help tickets | Open any chat --> clicking mark as resolved button twice should change status back to open |  | Resolved
42 | Admin | Customer support | Review content | Moderation Suite page opens |  | Reopen
43 | Seller | Login |  | Fix email field placeholder |  | Reopen
44 | Seller | Login |  | App logo missing |  | Reopen
45 | Seller | Login |  | Text alignment should be fixed for register store |  | Closed
46 | Seller | Login |  | fix footer text |  | Reopen
47 | Seller | Header | ALL | Header should match status bar theme |  | Reopen
48 | Seller | SignUp |  | Place holder should be properly visible of all fields |  | Reopen
49 | Seller | SignUp |  | Confirm OTP for email and phone number is getting out of container |  | Reopen
50 | Seller | SignUp |  | Didin't recive OTP message on phone number |  | Closed
51 | Seller | SignUp |  | fix footer text (Also been overlapped) |  | Reopen
52 | Seller | SignUp |  | Seller / Owner name field is accepting spaces as input |  | Closed
53 | Seller | SignUp |  | Shop / business name field is accepting spaces as input |  | Closed
54 | Seller | SignUp |  | Seller / Owner name field should have a character limit |  | Reopen
55 | Seller | SignUp |  | Business name field should have a character limit |  | Reopen
56 | Seller | SignUp |  | text getting out of box | https://prnt.sc/1wOK652wyghL | Reopen
57 | Seller | SignUp |  | password field should have maximun character limit |  | Reopen
58 | Seller | SignUp |  | Clicking next step button should proceed with one request only |  | Closed
59 | Seller | SignUp |  | Locality / area field takes space as input |  | Closed
60 | Seller | SignUp |  | City field takes space as input |  | Closed
61 | Seller | SignUp |  | State field takes space as input |  | Closed
62 | Seller | SignUp |  | Full address field takes space as input |  | Closed
63 | Seller | SignUp |  | Locality / area field takes only special character as input |  | Closed
64 | Seller | SignUp |  | step count is exceed on multiple clicks on next step button |  | Closed
65 | Seller | SignUp |  | Select on map field place holder is getting out of it's field |  | Closed
66 | Seller | SignUp | Select on map | select shop location container getting down the footer |  | Closed
67 | Seller | SignUp | Submit appliction | Text not visible | https://prnt.sc/4rTsuveWluHh | Closed
68 | Seller | SignUp | Submit appliction | Go too home is leading to user app |  | Resolved
69 | Seller |  |  | Add forget password functionality |  | Closed
70 | Seller |  |  | Admin didn't recive notification for new seller registration |  | Resolved
71 | Admin | Seller | Waiting for review | Back ground screen is scrolling |  | Resolved |  | please make sure it do not happen in any module
72 | Admin | Seller | Waiting for review | Filter by date button is not functional |  | Reopen
73 | Admin | Seller | Active sellers | No option to delete store |  | Closed
74 | Admin | Seller | Active sellers | View profile --> financial configuration --> fields take negative input |  | Reopen
75 | Seller | Profile |  | Profile photo is getting down the header |  | Closed
76 | Seller | Profile | Location & service setting | Change button getting out of the screen |  | Closed
77 | Seller | Dashboard |  | Dashboard card are not clickable |  | Closed
78 | Seller | Login |  | Make login possible with phone number as it is also verified during the signUp |  | Closed
79 | Seller | All | All | Search functionality missing |  | Closed
80 | Seller | Product | Add new product | Add next button at bottom to lead user to next step of form |  | Closed
81 | Seller | Product | Add new product | Sale price should give validation error on giving higher input than price |  | Reopen
82 | Seller | Product | Add new product | Details should not be lost on refresh |  | Closed
83 | Seller | Product | Add new product | Varients take negative input |  | Closed
84 | Seller | Product | Add new product | Camera clicked picture and video not accepted |  | Closed
85 | Seller | Product |  | Filter getting out of container |  | Reopen
86 | Seller | All | All | Page should open from top |  | Closed
87 | User | Login / signup |  | Logo should be fixed |  | Closed
88 | User | Login / signup |  | phone number field should take 10 numbers as input |  | Reopen
89 | User | Login |  | Login proceeded without signUp |  | Closed |  | it should redirect user to signup page if the number do not exist
90 | User | Profile |  | Logging out should ask for confirmation |  | Reopen
91 | User | Login / signup |  | Privacy policy redirect user to the home page |  | Closed
92 | User | SignUp |  | Name field should take only char as input |  | Closed
93 | User | Login |  | Logging in should open home page(currently its redirect to subscription plan page) |  | Reopen
94 | User | Home |  | Add padding (products and banners are sticking to the sides) |  | Reopen
95 | User | Home | Header | notification icon is missing |  | Reopen | not required
96 | User | Category | Header | notification icon is missing |  | Closed | not required
97 | User |  |  | all Pop up notification should be visible on the top / header side |  | Resolved
98 | User | Home | Any product | rate product --> only users user who purchased the product should be allowed to rate |  | Reopen
99 | User | Home | Any product | rate product --> keyboard automatically closes after entering one character |  | Reopen
100 | User | Home | Any product | rate product --> review entered for one item is visible in every product |  | Reopen
101 | User | Home | Any product | rate product --> submitted reviews are not visible |  | Resolved
102 | User |  | Any product | Clicking back (phone back button) works in background |  | New
103 | User | Home | Any product | One photo should slide at a time on sliding photos |  | Closed
104 | User | Home | Any product | cart price should show discounted price |  | Closed
105 | User | Home | Any product | share button should give options on which user can share |  | Reopen
106 | User | Cart | Any order | adding product from wishlist in cart do not display varient info |  | Reopen
107 | User | profile | Saved Address | add new --> add validation to name, phone number, address, city, state and pincode field |  | Closed
108 | User | profile | Saved Address | Add new --> save --> geocoding failed error shows up (but address saved successfully) |  | Closed
109 | User | profile | Saved Address | No option to make other saved address default |  | Closed
110 | User | profile | Saved Address | Refreshing page should not vanish pre filled information and add new address page should remain open |  | Closed
111 | User | profile | Saved Address | Same address saved twice |  | Closed
112 | User | profile | Saved Address | Deleted address stays until refreshed |  | Resolved
113 | User | profile | Edit (seva fast card) | edited info did not update |  | Resolved |  | Updating on refresh
114 | User | profile | Seva fast card | Fix alignment | https://prnt.sc/sbrN9GhjkKcP | Resolved
115 | User | Profile | Wishlist | Wislisted product do not show base discount (only dbt discount is shown) |  | Resolved
116 | User | Profile | help and support | call us and email option are not functional (they should redirect user to the phone and email app respectively) |  | Resolved
117 | User |  |  | No option to save new address using current location |  | Resolved
118 | User | Profile | Privacy policy | Privacy policy is repeated is already in help and support |  | Resolved
119 | Delivery | Header | All | Header should match the theam of status bar |  | Resolved
120 | Delivery | Login / SignUp |  | Logo should be fixed / pinned |  | Reopen
121 | Delivery | Login / SignUp |  | There should be a single logo on the login page |  | Closed
122 | Delivery | Login / SignUp |  | shitching between the login and signup should not let user losse the filled details |  | Reopen
123 | Delivery | SignUp |  | Terms & privacy policy are not clickable |  | Closed
124 | Delivery | SignUp | Personal info | Full name field should take only characters as input and only spaces are also being taken as input |  | Closed
125 | Delivery | SignUp | Personal info | email field should give validation error for wrong input in real time |  | Resolved
126 | Delivery | SignUp | Personal info | Parmanent address field should give validation error on invalid input (for eg. @@@) and only spaces are also being taken as input |  | Closed
127 | Delivery | SignUp | Vehicle info | If cycle is selected in vehicle type than field should change accordingly |  | Closed |  | remove by developer
128 | Delivery | SignUp | Vehicle info | Driving licance number should take input in valid format only |  | Closed
129 | Delivery | SignUp | Vehicle info | Vehicle registration number should not take invalid input |  | Closed
130 | Delivery | SignUp | Bank info | PAN card number field should give validation error on wrong input in real time |  | Closed
131 | Delivery | SignUp | Bank info | Account holder name field should take only characters as input and it should also not take only spaces as input |  | Closed
132 | Delivery | SignUp | Bank info | Account number field should take input in format (9-18) |  | Closed
133 | Delivery | SignUp | Bank info | IFSC Code field should take input in valid format only and give validation error in real time |  | Closed
134 | Delivery |  |  | Delivery partner logged in without admin approval |  | Closed
135 | Delivery | Delivery Drivers | Waiting for review | Filters are not working |  | Reopen
136 | Delivery | Delivery Drivers | Active Drivers | edit should show existing info |  | Resolved
137 | Delivery | Profile |  | Notification bell is not clickable |  | Resolved
138 | Delivery | Earning |  | Download icon not working |  | Resolved
139 | Delivery |  |  | every pop up notification is visible on both header and footer side |  | Resolved
140 | Delivery | profile | personal details | DOB and blood group details are not asked during signup |  | Resolved
141 | Delivery | profile | personal details | DOB date format should be in DD/MM/YYYY |  | Resolved
142 | Delivery | profile | All | Page should open from top |  | Resolved
143 | Delivery | Profile | Bank account | bank Card not visible |  | Resolved
144 | Delivery | Profile | Documents | Not been able to upload police clearance |  | Resolved
145 | Delivery | Profile | Documents | Not been able to upload bank passbook |  | Resolved
146 | Delivery | Login | Verify OTP | Terms of sevices and privacy policy are not clickable |  | Resolved
147 | Delivery | Profile | Safety & privacy | Delete emergency contacts --> refresh --> they reappear again |  | Resolved
148 | Delivery | Profile | Safety & privacy | Add new contact --> Name field should take only character as input |  | Resolved
149 | Delivery | Profile | Safety & privacy | Add new contact --> phone number field should take only 10 numbers as input |  | Resolved
150 | Delivery | Profile | Settings | Dark mode not working |  | Resolved
151 | Delivery | Profile | Help & Support | Fix alignment | https://prnt.sc/N54z8hKJcHbg | Resolved
152 | Delivery | Profile | Help & Support | button below Still need help is not working |  | Resolved
153 | Seller |  |  | Seller app didn't recive order request when closed |  | Resolved
154 | Seller |  |  | Back ground screen is scrolling when order screen pops up |  | Resolved
155 | Seller | Dashboard | total revenue card | Revenue updated just after accepting order (COD ..money didn't recived yet) |  | Resolved
156 | Delivery |  |  | Didn't recive Request when app is closed |  | Resolved
157 | Seller | Orders |  | Accepted order not visible until refreshed |  | Resolved
158 | Delivery | Login |  | Delivery partner login is use less without referal code so referal should be mandatory in both login and signUp case |  | Resolved | The Referral/Seller code is already mandatory on the Signup (Registration) page. Once a Delivery Partner is registered, their phone number is permanently linked to the specific Seller in our database. Therefore, asking for the Referral code again during Login is logically redundant and will create a poor user experience. The system already identifies the associated Seller using their registered phone number. Hence, this change is not required."
159 | Delivery | SignUp | Application pending screen | Text not visible |  | Resolved
160 | Delivery | SignUp | Application pending screen | Go too home is leading to user app |  | Resolved
161 | Admin | Delivery drivers | Active drivers | Active drivers so riders who are pending for approval |  | Resolved
162 | User |  |  | Return flow is not there |  | Resolved | it is already there
163 | Delivery |  |  | Delivery partner do not receive any pop up for delivery order even if the app is open |  | Resolved
164 | Admin | Fee & charges | Main charges | platform / handling fee and free delivery minimum is takeing negative value as input |  | Resolved
165 | Admin | Fee & charges | distance based | Base distance capacity not changable with increment and decrement arrow |  | Resolved
166 | Admin | Fee & charges | Distance based | All fields except return delivery commission are taking negative value as input |  | Resolved
167 | Admin | Setting | General | Support phone number takes char as input |  | Resolved
168 | Admin | Orders | view details(any order) | Price details should be completely visible (platform fee missing) |  | Resolved
169 | Admin | Seller | Seller location | Scroll is not there for store section | https://prnt.sc/i2WpzzOKhgfC | Resolved
170 | Admin | Seller | Seller location | All categories filter --> general --> filter stucks and options within it also disappears |  | Resolved
171 | Admin | Seller | Active seller | Pagination not working | https://prnt.sc/Lb7A5AMOvjZm | Resolved
172 | Admin | Delivery drivers | Active drivers | Add new rider --> Add validation name, phone number, vhecile number and operational area field |  | Resolved
173 | Admin | Delivery drivers | Active drivers | Add new rider --> if work vhecile is bicycle than fields should change accordingly |  | Resolved
174 | Admin | Delivery drivers | Active drivers | Edit any rider --> save --> no pop up for successful update |  | Resolved
175 | Delivery | History | any order card | Zero is not visible in order amount in the history section | https://prnt.sc/L7hD4lGZoSXg | Resolved |  | amount was 950 and 1430
176 | Admin | Wallet |  | green dot appers to white |  | Resolved
177 | Admin | Wallet | settlement | Bulk settlement button is not visible |  | Resolved
178 | Admin | Money request |  | export all button is not functional |  | Resolved
179 | Admin | Seller payments |  | Download master ledger is not working |  | Resolved
180 | Admin | Seller payments |  | revenue insights is not working |  | Resolved
181 | Admin | Seller payments | action | view --> download voucher --> transation ID is too long and getting out of the page |  | Resolved
182 | Admin | Seller payments | action | edit --> share or redirection button is not working |  | Resolved
183 | Admin | Collect cash | settle (management) | Amount is going negative |  | Resolved
184 | Admin | Collect cash | view (management) | field not visible |  | Resolved
185 | Admin | Collect cash |  | setteling amount is adding negative amount in riders cash statistics |  | Resolved
186 | Delivery |  |  | Order request still stays even after time ends (continously rings too) |  | Resolved
187 | Delivery | Earnings |  | Today and weekly filters are not required if rider is being paid monthly |  | Resolved
188 | User | Home |  | Displaying wrong base pricing (1000 varient price is 900) | https://prnt.sc/RlBwWF20h-9d | Resolved
189 | Admin |  |  | Return request notification to admin opens local host | https://prnt.sc/vmoU0c2rBQ8W | Resolved
190 | Seller | products | add new product | when creating a new product a unique SKU code should be auto generated (when the initial characters are same as already existing product that it generate a duplicate SKU code |  | Resolved
191 | Seller |  |  | Seller didn't recive any notification for approval or rejection of account |  | Resolved
192 | User | SignUp |  | Already existing user is still able to signUp with same credentials |  | Resolved
193 | User | Home | Any product | Product details are static / same in all products |  | Resolved
194 | User | checkout |  | Adding global and local product in cart gives wrong price details (delivery charge, handleing fee) and also user unable to unable to order (slide to place order is not working in this case) |  | Resolved
195 | User | checkout |  | RazorPay not working |  | Resolved
196 | User | SignUp |  | SignUp proceed with already existing number |  | Resolved
197 | Seller | Products |  | out of stock filter is not working |  | Resolved
198 | Seller | products | all approvals | product dont need approval from admin so there is no need of this filter |  | Resolved
199 | Seller | Products | Filter | filter screen is getting out |  | Resolved
200 | Delivery |  |  | no notification to on admin panel for new rider registration |  | Resolved
201 | Admin | Delivery drivers | waiting for review | vehicle info not visible in application |  | Resolved
202 | Delivery |  |  | Delivery partner didn't recive any notification for approval or rejection of account |  | Resolved
203 | Delivery | Home |  | Delivery partner profile picture is not visible on home screen |  | Resolved
204 | Delivery | Home |  | ID is different from profile page |  | Resolved
205 | Delivery | Checkout |  | your wishlist product is not being added in the cart |  | Resolved
206 | Seller |  |  | Seller should be notified with a ring if app is closed |  | New |  | flutter
207 | Delivery |  |  | Delivery partner should be notified with a ring if app is closed |  | New |  | flutterr
208 | Seller | Orders |  | status not updating for orders in real time |  | Resolved
209 | Seller | Orders |  | Earning amount is not correct |  | Resolved
210 | User | Orders |  | Status is not updating in real time |  | Resolved
211 | User | Orders |  | return request can only be done within 2 min |  | New
212 | Seller | Dashboard |  | total revenuse is not correct |  | Resolved
213 | Seller | Orders |  | Orders status can not be updated to confirmed |  | Resolved
214 | Seller | Orders |  | Timed out order directly gets confirmed |  | Resolved
215 | Seller | Orders |  | delivery partner assigned without updating status to packed |  | Resolved
216 | Seller | Orders |  | Return request is not visible in product card and product details |  | Resolved
217 | Seller | Orders |  | OTP for product return is not visible to seller |  | Resolved |  | Return flow not complete
218 | Delivery | History | any order (with return request) | delivery partner get return request without seller approval |  | Resolved
219 | User | Checkout | Order page | estimated and arrriving time are refering to same time so keep one (keep arriving time) |  | Resolved
220 | User | Checkout | Order page | delivery partner should not be visible to user until not assigned |  | Resolved
221 | Delivery | History |  | Order delivery request automatically set to confirmed even if the delivery partner do not accept it |  | Resolved
222 | Delivery | History | order cards | Distance time are static on order card |  | Resolved
223 | Delivery, User |  |  | arriving time should be same on both delivery and user side (it happens sometimes and on multiple refresh it starts to show similar time again) |  | Resolved
224 | Delivery | History | order page | numbers on the confirmed and out of delivery are not visible |  | Resolved
225 | Seller | Orders |  | order status should not be reversed once delivered |  | Resolved
226 | Delivery | History | Order page | entey delivery OTP --> submit otp button nut visible |  | Resolved
227 | User | Checkout |  | when using wallet money the place order scroll in the bottom should not show free order because user is still paying for it. It's just the method of payment changed |  | Resolved
228 | User | Checkout |  | order amount should not be zero in the order summary |  | Resolved
229 | Delivery | History | Order page | customer details card should not show cash as the payment is donr through wallet |  | Resolved
230 | Seller , User |  |  | status do not update to picked up after picking order from customer |  | Resolved
231 | Delivery | History | order page | return drop card shows cash and bill amount during return flow |  | Resolved
232 | Delivery |  |  | return OTP is recived on the phone number instead of in the return section |  | Resolved
233 | User | Profile | My orders | status overlaps the order ID |  | Resolved
234 | Seller | Dashboard |  | Seller revenue should be deducted on product return |  | Resolved
235 | Admin | Orders | Return requests | User recives the return amount multiple times on muliple clicks on Approving return QC |  | Resolved
236 | User | Profile |  | Clicking notification bell gives error |  | Resolved
237 | User | Profile | Order transactions | it only shows debited amounts with the credited logo |  | Resolved
238 | User | home |  | Adding item from different store should ask user to replace existing item as user can not order from multiple store at a time |  | Resolved
239 | User | Services | Register / Manage profile | Full name field should take only characters as input |  | Resolved
240 | User | Services | Register / Manage profile | clicking phone number field should open number keyboard |  | Resolved
241 | User | Services | Register / Manage profile | Operational city field should take only characters as input |  | Resolved
242 | User | Services | Register / Manage profile | email field should give validation error for wrong input in real time |  | Resolved
243 | User | Services | Register / Manage profile | Action required for listing --> pay now --> payment initiation failed |  | Resolved |  | Service flow stops at payment step
244 | User | Services | Register / Manage profile | Add / edit service --> service that are free in admin panel shows paid in user app |  | Resolved
245 | User | Services | Register / Manage profile | service price catalog --> pricing should not take negative input |  | Resolved
246 | User | Services |  | CIty field should take only character as input |  | Resolved
247 | User | Services | Register / Manage profile | service price catalog --> add service --> added service do not save |  | Resolved
248 | User | Services | Register / Manage profile | Promotional banner --> create ad request --> target operational city should take only character as input |  | Resolved
249 | User | Services | Register / Manage profile | Promotional banner --> create ad request --> choose media type as image --> camera clicked image should be accepted |  | Resolved
250 | User | Services | Register / Manage profile | Promotional banner --> create ad request --> pay and submit request payment initiation failed |  | Resolved
251 | User | Services | Register / Manage profile | Promotional banner --> create ad request with long title --> title name is getting out of its container |  | Resolved
252 | User | Services | Register / Manage profile | Promotional banner --> add edit option for already created banners |  | Resolved
253 | User | Plans |  | Payment initiation failed for subscription |  | Resolved
254 | Admin | Sub admin | Create new sub admin | Full name field should take only character as input |  | Resolved
255 | Admin | Sub admin |  | Deleted sub admin do not automatically lose access to admin panel in real time |  | Resolved
256 | Admin | Sub admin |  | Sub admin is not able to access any all data that is accesable |  | Resolved
257 | Admin | Subscription plans | create new | add validation to all the fields |  | Resolved
258 | Admin | Subscription plans |  | filter and more button are not functional |  | Resolved
259 | User | profile | custom photo order | City field should take only character as input |  | Resolved
260 | User | profile | custom photo order | Camera clicked picture not accepted |  | Resolved
New
261 | User | profile |  | there is no way to see photo order history |  | New
262 | User | login |  | click on Terms & conditions & privacy policy --> should not show footer menu |  | New
263 | User | login/sign up | change for all app | phone no. filed should accept valid indian no. starts with 6,7,8,9 |  | New
264 | User | sign up |  | Add resend OTP timer |  | New
265 | User | sign up |  | footer menu should be fixed | https://prnt.sc/l8ZfBYClPWUl | New
266 | User | home |  | banner & categories are overlap | https://prnt.sc/0tUtd75zGaC2 | New
267 | Seller | login |  | enter new credentials which is not registered, should show --> store not register with this email, registered first |  | New
268 | Admin |  |  | fevicon logo is very small |  | New
269 | Seller | login/sign up |  | all filed placeholder should be fully visible & entered details also |  | New
270 | Seller | sign up |  | invalid referral code works, should show validation |  | New
271 | Admin |  |  | auto log outing admin |  | New
272 | Seller | login |  | email should accept in format |  | New
273 | Seller | sign up |  | your seller application is under review page --> there is 2 similar text back to seller login & go to seller login, remove one |  | New
274 | Admin | category |  | add header category --> background should not be scrollable |  | New
275 | Delivery | sign up |  | fill details, click on terms & privacy policy --> then back to registeration page filled details should not be removed & redirect to same page |  | New
276 | Delivery | sign up /login |  | when enter details page should be automatically scrollable |  | New
277 | Delivery | sign up |  | on refreshing page should be redirect to same page & should not remove filled details |  | New
278 | Delivery | sign up |  | invalid seller invite code works --> it should give validation on same page |  | New
279 | Delivery |  |  | click on Terms & conditions & privacy policy --> should not show footer menu |  | New
280 | Delivery |  |  | back from otp page it should redirect to previous page |  | New
281 | Admin | delivery |  | waiting for review --> view application --> background should not be scrollable |  | New
282 | Delivery | sign up |  | there is no filed of experience, Preferred Area on registration |  | New
283 | Admin | delivery |  | all filled details should show on admin( waiting for review --> view application) |  | New
284 | Seller | home |  | footer menu colour should same according to theme |  | New
285 | Seller | product | add | when enter details, footer menu should be fixed at bottom |  | New
286 | Seller | product | add | next button is not visible |  | New
287 | Seller | product | add | there is no gallery option/pick from library, to upload file |  | New
288 | Seller | product | edit | previous uploaded images should show |  | New
289 | Seller | product | filter | newest filter going out of page |  | New
290 | User | home |  | showing default address |  | New
291 | User | home |  | when open user app --> first should show location pop up |  | New
292 | User | home | location | add --> new address --> already filled phone no. --> save address , showing validation enter valid no. |  | New
293 | User | home | location | add --> new address --> filled no. not saved |  | New
294 | Seller |  |  | location--> should show area name |  | New
295 | Seller |  |  | select shop location not working |  | New
296 | User | home |  | showing static delivery time |  | New
297 | User | home |  | product --> click --> it should show product detail (for choosing varient) |  | New
298 | User | home |  | product add with varients --> showing your cart contains items from another store |  | New
299 | Seller |  |  | not coming order alert sound |  | New
300 | User | order details |  | click on invoice --> minimize the length of order id |  | New
301 | User | order details |  | click on invoice --> print --> open 4 duplicate pages with incomplete details |  | New
302 | User | order details |  | reached 60 second --> not showing cancelled status |  | New
303 | User |  |  | seller app sometime redirect to user app |  | New
304 | Delivery |  |  | new task --> not showing delivery earning |  | New
305 | Delivery |  |  | new task --> remove static note(handle eggs) |  | New
306 | Delivery |  |  | new task --> customer details --> chat icon is not clickable |  | New
307 | User |  |  | after order delivered --> should show ratings |  | New
308 | Seller |  |  | order details --> not showing delivery address |  | New
309 | Seller |  |  | once order delivered --> it can't go back to change previous status |  | New
310 | Seller |  |  | payment calculation going wrong --> showing wrong earning |  | New
311 | Admin |  |  | not showing seller revenue |  | New
312 | Seller | products |  | Search product, if not availabke, should show no product available |  | New
313 | User | Any product |  | unable to write a purchased product review |  | New
314 | User | Any product |  | when write review --> product amount & view cart section should be fixed in bottom |  | New